## TASKS
Tasks
Brief Description | Related Issues | START DATE | DUE DATE | % COMPLETE | DONE | Notes
Create vehicle models | 8, 12, 14 | 2020-06-17 | 2020-06-26 | 75% | 0 | Small tweaks to add to SLS, need to rework Blue Moon Lander
Create world save file | 13 | 2020-06-17 | 2020-06-26 | 50% | 0 | Just needs vehicles placed in correct orbits
Upload mod list |  | 2020-06-23 | 2020-06-26 | 75% | 0 | Just requires a double-check that everything's included
Have groups create issues |  | 2020-06-24 | 2020-06-28 | 25% | 0 | Have each group create issues for all their development tasks
0
0
0
0
0
0
0
0